# LEP end-to-end — Live plan

Dates: 12 October 2026 (Mon) → 17 October 2026 (Sat)

Goal: LEP Program Journey is live for a pilot batch by end of 17 Oct 2026 — login → pre-work → sessions → tasks → rituals → reminders (app + staff alerts) → status.

Live means: One real or staging batch has session times set; participants receive automated reminders; CEM receives C-alerts; rituals + weekly score work; mandatory items show red when overdue. MBW / 100BM are out of scope for this week.

# Definition of Live (exit criteria — 17 Oct)

Staff can save CMS events + upload content (rules already deployed).

Pilot batch: Day 1 date + S0–S13 times/join links configurable.

T01–T27 mapped; T02/T03/T12/T20 marked mandatory with due anchors.

Participant auto: WELCOME, PAY, session R-24h / R-1h / R-10m, POST/CATCHUP, rituals AM/PM, SCORE, task due/overdue.

Staff auto: C01–C24 alerts to CEM/PL (email or in-app) — human calls still by CEM.

App: status-based LEP home + rituals check-in + Sat scoreboard.

E2E smoke: phone login → Zoho access → open task → tick rituals → receive test push/WA.

PL/CEM signed: pilot batch go-live checklist.

# Day-by-day plan

| Date | Day | Focus | Tasks (end-to-end LEP) | Owner | Done when |
| --- | --- | --- | --- | --- | --- |
| 12-10-2026 | Mon | Foundation + map | 1) Staff CMS login test (save event + upload file). 2) T01–T27 ↔ programCourseSlice mapping sheet (mandatory/optional + due). 3) Add C24 + optional FT/PTW rules to CMS defaults. 4) Fix Cloud Functions deploy (discovery timeout / Node) — confirm resolvePhoneAccess + refreshMyAccess. 5) Lock pilot batch name + Day 1 Saturday date with CEM/PL. | Tech + CEM | CMS write works; mapping sheet approved; functions up; pilot batch named |
| 13-10-2026 | Tue | Calendar + journey data | 1) Batch session times editor (S0–S13, start/end, join link) — MVP in admin or app. 2) Enter pilot batch session times (IST defaults from LEP_FLOW). 3) Wire tasks: mandatory flags + due relative to Day 1 / sessions. 4) BHAG prefilled form + Day 2 CoDeSeF download path on home. 5) Rename visible “course” → Program Journey on LEP screens. | Tech + CEM | Pilot calendar saved; mandatory tasks show dues; CoDeSeF path works |
| 14-10-2026 | Wed | Send engine — sessions | 1) Scheduler reads cms_notificationEvents + batch calendar. 2) Live: R-24h, R-1h, R-10m (core); OPT-5PM + OPT-R-10m (FT/PTW). 3) Quiet hours + daily cap ≤3 (R-10m free). 4) POST (attended) + CATCHUP (absent) 30 min after session. 5) Test sends on staging numbers (push + WhatsApp template). | Tech | Test participant gets R-1h / R-10m for a test session |
| 15-10-2026 | Thu | Tasks, rituals, status | 1) WELCOME + PAY on enrollment; pre-work Wed/Thu reminders. 2) TASK-DUE / TASK-OVERDUE / MAND-OVERDUE (red only for T02/T03/T12/T20). 3) Rituals daily check-in in app + RITUALS-AM / RITUALS-PM. 4) Status home: Registered / Pre-program / Ready / Active / Needs attention. 5) CMS content linked to tasks (published items on task screen). | Tech | Rituals save; mandatory overdue turns red; welcome fires on test enroll |
| 16-10-2026 | Fri | CEM alerts + score | 1) Staff alerts C01–C24 to CEM/PL/Sales (email or admin inbox). 2) SCORE Sat 12:00 + CEM C16 12:30 (can simulate “Saturday” in staging). 3) C04 poster reminder (CEM still sends poster by hand). 4) E2E dry run with CEM: new enroll → pre-work → fake session → absentee. 5) Fix P0 bugs from dry run. | Tech + CEM | CEM receives at least C01, C11 sample, C13/C15 on test triggers |
| 17-10-2026 | Sat | GO LIVE | 1) Full E2E checklist on production (or prod-like staging). 2) Publish weekly scoreboard path; back-fill until 11:59 AM rule on. 3) PL/CEM sign-off on pilot batch. 4) Flip pilot batch to LIVE; monitor first real R-24h/R-1h. 5) Hotfix only — no MBW/100BM work this day. 6) Write short go-live note: what is live vs still human (calls/poster). | Tech + PL + CEM | LEP LIVE for pilot batch — signed checklist |

# E2E checklist (run 16–17 Oct)

| # | Step | Pass? |
| --- | --- | --- |
| 1 | Phone login → Zoho resolvePhoneAccess → correct program unlocked |  |
| 2 | Enrollment triggers WELCOME (+ PAY if unpaid) |  |
| 3 | Open VIA / B-HAG / info form; due shows; incomplete stays available (no lock) |  |
| 4 | Home shows correct status + Orientation / Day 1 countdown |  |
| 5 | Session join link from R-1h / R-10m opens |  |
| 6 | Mark attended → POST; mark absent → CATCHUP + recording |  |
| 7 | Tick 5 Rituals; miss a day → back-fill before Sat 11:59 AM |  |
| 8 | Sat SCORE on app + WhatsApp; CEM gets C16 |  |
| 9 | Mandatory overdue → red + MAND-OVERDUE + CEM C13 |  |
| 10 | CEM gets C01 on new enroll; can open batch CoDeSeF view |  |
| 11 | Upload task file to lep/{uid}/… succeeds under Storage rules |  |
| 12 | Quiet hours / daily cap respected on test schedule |  |

# Still human after go-live (not automated this week)

CEM welcome call, no-show calls, overdue personal calls, ritual WhatsApp check-in

Poster template send (C04 only reminds CEM)

Payment chase calls (Sales)

Quiz finalisation with Arshi

Certification decision / certificate generation ops

# Out of scope this week (after 17 Oct)

MBW requirement + flow sign-off and build

100BM requirement + flow sign-off and build

Desktop walking companion / widgets

Full multi-batch CEM console polish

Target date: LEP end-to-end LIVE for pilot batch by 17-10-2026.