# LEP journey — simple guide for the team

For: CEM, Program Lead, Sales, Admin — no technical background needed.

Go-live week: Monday 12 October 2026 → Saturday 17 October 2026

By Saturday 17 October, one pilot LEP batch should be running on the app: learners get automatic reminders, and CEM gets clear alerts about who needs a call.

# 1. What is the LEP Program Journey? (in plain words)

LEP is a roughly 4-week leadership program. Learners attend live sessions (starting with Orientation on Thursday, then two full days on weekend, then weekly sessions), complete a few important tasks, and practise 5 daily rituals.

Almost everything is optional for learning. Only three things are must-do for the certificate:

VIA Survey (strengths assessment)

B-HAG — their big goal (written early, then filled into CoDeSeF)

Shameless Pitch statement (short pitch)

If those three are late, the app shows them in red and asks CEM to follow up. Other tasks never block the learner and never turn the whole journey red.

# 2. How a learner moves through the program

Think of it as stages on their home screen:

| Stage | When it happens | What they see on the app | Main button |
| --- | --- | --- | --- |
| Registered | They paid registration but may still owe balance | Payment banner, welcome video, Orientation date, short pre-work list | Pay now |
| Pre-program | Info form, B-HAG or VIA still open | Pre-work checklist with due dates + countdown to Orientation | Continue pre-work |
| Ready to start | Pre-work finished | Next session card with join link + journey map | Add Day 1 to calendar |
| Active — on track | No overdue must-do items | Today’s session/tasks, daily rituals, weekly score, recordings | Tick today’s rituals |
| Active — needs attention | VIA, B-HAG or Pitch overdue, or a main session missed | Same as Active, plus a red list of what is late | Catch up now |
| Completed — certified | Graduation done + 3 must-dos done | Certificate, final score, alumni next steps | Download certificate |
| Completed — certificate pending | Graduation done but a must-do still open | Pending list + grace deadline + CEM contact | Complete pending items |

# 3. What the app does by itself vs what CEM does

Simple rule: the app sends reminders and alerts. CEM still makes the human calls and sends the poster.

| The app does automatically | CEM / team still does by hand |
| --- | --- |
| Welcome message when someone joins | Welcome phone call within 24 hours |
| Reminders before each session (1 day, 1 hour, 10 minutes) with join link | Call people who did not join; share the recording |
| Reminders for VIA, B-HAG, Pitch when due or late | Personal call if a must-do is still late after 2 days |
| Daily morning nudge for 5 Rituals; weekly score every Saturday | WhatsApp check-in if someone skips rituals for 3 days |
| Alert to CEM: “send poster template” | Actually send the poster with quotation to the batch |
| Alert to CEM + Sales: payment still pending | Payment follow-up calls |
| Daily digest: who is at risk (must-dos, rituals, absences) | Decide whom to call and log the outcome |
| Optional Friday “Prepare to Win” / Fast Track: short same-day reminder only | No chasing for optional sessions — recording goes to the app |

# 4. Sessions in one glance (times can change per batch)

CEM or PL sets the real dates and Zoom links for each batch. When a session moves, reminders move with it.

| Session | Type | Usual timing |
| --- | --- | --- |
| Orientation | Main | Thursday before Day 1, evening |
| Day 1 & Day 2 (full days) | Main | Weekend after Orientation |
| Closure / Review | Main | Week 1 Tuesday evening |
| Fast Track | Optional | Week 1 Thursday evening |
| Prepare to Win (×4) | Optional | Friday evenings, Weeks 1–4 |
| Differentiated Brand | Main | Week 1 Saturday morning |
| Progress Check | Main | Week 2 Wednesday evening (default) |
| Shameless Pitch | Main | Week 2 Saturday evening |
| Leadership Habits | Main | Week 3 Saturday morning |
| Graduation | Main | Week 4 Saturday evening |

# 5. This week — what happens each day (12–17 Oct)

This is the go-live week for one pilot LEP batch. Written for everyone on the team.

| Date | In simple words — what we finish | What CEM / PL need to do |
| --- | --- | --- |
| Mon 12 Oct | Confirm the app admin can save messages and files. Agree the list of all learner tasks (which 3 are must-do). Choose the pilot batch and its Day 1 Saturday date. | Name the pilot batch. Confirm Day 1 date. Share any Zoom links you already have. |
| Tue 13 Oct | Put all session dates, times and join links into the system for that batch. Make sure B-HAG and CoDeSeF download work on the home screen. | Enter or approve the full session calendar for the pilot batch. Check that Orientation and Day 1/2 look right. |
| Wed 14 Oct | Turn on automatic session reminders (tomorrow / 1 hour / 10 minutes before). Test that a sample learner phone gets the messages. | Give 1–2 test mobile numbers. Confirm the reminder wording feels right (inspiring, not robotic). |
| Thu 15 Oct | Turn on pre-work and task reminders, daily rituals in the app, and the home screen stages (Registered → Needs attention, etc.). | Walk through the app as a learner once. Say if anything is confusing on the home screen. |
| Fri 16 Oct | Turn on CEM alerts (new join, no-shows, late must-dos, daily digest). Dry run with CEM: fake a late task and a missed session. | Join the dry run. Practise: you get an alert → you make the call. Confirm the poster reminder is clear (you still send the poster). |
| Sat 17 Oct — LIVE | Final check. Pilot batch goes live. Weekly rituals score path ready. Watch the first real reminders. | Sign off: “Yes, this batch can run on the app.” Be ready for welcome calls on new joins. |

# 6. How you will know it is live (17 Oct)

Pilot batch calendar (dates + join links) is filled in.

A test learner gets session reminders on phone (app and/or WhatsApp).

CEM gets an alert when someone new joins or a must-do is late.

Learner can tick daily rituals; Saturday score is ready to show.

Home screen shows the right stage (for example “Needs attention” if VIA is late).

PL and CEM have signed the short go-live checklist.

# 7. What we are not doing this week

So the team stays focused: this week is LEP only for one pilot batch.

Full MBW program build

Full 100 Board Members program build

Replacing CEM phone calls with robots (calls stay human)

Quiz final content (still with Arshi after go-live)

Remember: App reminds. CEM connects. Together that is the LEP journey for the learner.

Target: Pilot LEP batch LIVE by Saturday 17 October 2026.