## Mandatory locked
LEP tasks — Mandatory vs Optional (from LEP_FLOW v1.5)
Source: LEP_FLOW.pdf v1.5 · 3 mandatory FINALIZED · Due = Friday of that week (go-live week 12–17 Oct 2026)
THE ONLY 3 MANDATORY ITEMS (red + certificate)
ID | What | Due | Why it matters
T03 | VIA Survey | Pre-program Friday (end of pre-program week) | Must-do — strengths assessment
T02 + T12 | B-HAG form + B-HAG in CoDeSeF | T02: Pre-program Friday · T12: Week 1 Friday | Must-do — one B-HAG across form + sheet
T20 | Shameless Pitch statement (60 sec) | Week 2 Friday | Must-do — pitch
Rules everyone agrees
1. Only T02/T12 (B-HAG), T03 (VIA), T20 (Pitch) are mandatory.
2. Everything else is optional — never locks the next step, never turns status red.
3. T04 payment is admin/Sales — not a learning must-do.
4. T25 quiz still to finalise with Arshi — optional until PL decides.
5. T26 daily rituals optional for certificate unless PL says otherwise; still scored every Saturday.
6. CEM: 3 mandatory FINALIZED — due Friday of that week (T02/T03 pre-program Fri; T12 W1 Fri; T20 W2 Fri).
CEM / PL: FINALIZED — dues = Friday of that week
Name: FINALIZED Date: 12 Oct 2026 Rule: Friday of that week

## T01-T27 Tasks
ID | Task / activity | Type | Mandatory? | Opens | Do by (from LEP_FLOW) | Verified by | Notes for CEM | Do by (PDF exact)
T01 | Participant Information Form | Form | Optional | On enrollment | Pre-program Wednesday, 8:00 PM IST (day before Orientation) | Auto | Nice to have; not red if late | Pre-program Wed, 8:00 PM
T02 | B-HAG form (name/email/phone prefilled) | Form | Mandatory | On enrollment | Pre-program Friday (end of pre-program week) | CEM | Must-do #1 part A — discussed at Orientation · Due Friday of that week (finalized). | Pre-program Fri
T03 | VIA Survey | Survey + PDF upload | Mandatory | On enrollment | Pre-program Friday (end of pre-program week) | Auto | Must-do #2 · Due Friday of that week (finalized). | Pre-program Fri
T04 | Payment of balance (if pending) | Payment (admin) | Admin / payment | On enrollment | Pre-program Wednesday, 8:00 PM IST (day before Orientation) | Admin | Not a learning task; Sales/Admin chase | Pre-program Wed, 8:00 PM
T05 | Affirmation | Task | Optional | Week 0 Saturday, 7:30 PM (after Day 1) | Week 1 Monday, 9:00 PM IST | — |  | Week 1 Mon, 9:00 PM
T06 | PEG table | Task | Optional | Week 0 Saturday, 7:30 PM (after Day 1) | Week 1 Monday, 9:00 PM IST | CEM |  | Week 1 Mon, 9:00 PM
T07 | Download CoDeSeF sheet (B-HAG prefilled) | Download | Optional | Week 0 Sunday, 7:30 PM (after Day 2) | Week 1 Tuesday, 6:00 PM IST | Auto | Day 2 sheet with B-HAG printed | Week 1 Tue, 6:00 PM
T08 | Self-awareness game (beliefs) | Task | Optional | Week 1 Monday, 10:00 AM | Week 1 Tuesday, 6:00 PM IST | CEM |  | Week 1 Tue, 6:00 PM
T09 | Instances game table | Task | Optional | Week 1 Monday, 10:00 AM | Week 1 Tuesday, 6:00 PM IST | CEM |  | Week 1 Tue, 6:00 PM
T10 | ERRC drift (from Day 1 session) | Task | Optional | Week 1 Monday, 10:00 AM | Week 1 Tuesday, 6:00 PM IST | CEM |  | Week 1 Tue, 6:00 PM
T11 | Crucibles of Leadership | Task | Optional | Week 1 Monday, 10:00 AM | Week 1 Tuesday, 6:00 PM IST | CEM |  | Week 1 Tue, 6:00 PM
T12 | B-HAG in CoDeSeF (complete up to B-HAG) | Form / sheet | Mandatory | Week 1 Monday, 10:00 AM | Week 1 Friday | CEM | Must-do #1 part B — with T02 = full B-HAG · Due Friday of that week (finalized). | Week 1 Fri
T13 | Powerful Extreme Responding | Task | Optional | Week 1 Tuesday, 9:00 PM (after Closure session) | Week 1 Thursday, 9:00 PM IST | CEM |  | Week 1 Thu, 9:00 PM
T14 | Purpose PEG table | Task | Optional | Week 1 Tuesday, 9:00 PM (after Closure session) | Week 1 Thursday, 9:00 PM IST | CEM |  | Week 1 Thu, 9:00 PM
T15 | Day 2 assignment | Task | Optional | Week 1 Tuesday, 9:00 PM (after Closure session) | Week 1 Thursday, 9:00 PM IST | CEM |  | Week 1 Thu, 9:00 PM
T16 | Read VIA report (bring to S4) | Reading | Optional | Week 1 Thursday, 10:00 AM | Week 1 Saturday, 9:00 AM IST (before Differentiated Brand) | — | Bring to Differentiated Brand | Week 1 Sat, 9:00 AM
T17 | Differentiated Brand statement / video | Upload | Optional | Week 1 Saturday, 11:30 AM (after Differentiated Brand) | Week 2 Monday, 8:00 PM IST | PL or CEM | Soft follow-up only | Week 2 Mon, 8:00 PM
T18 | Resume update (27 Principles) | Task | Optional | Week 2 Monday, 10:00 AM | Week 2 Thursday, 9:00 PM IST | — |  | Week 2 Thu, 9:00 PM
T19 | LinkedIn profile update | Task | Optional | Week 2 Tuesday, 10:00 AM | Week 2 Thursday, 9:00 PM IST | — |  | Week 2 Thu, 9:00 PM
T20 | Shameless Pitch statement (60 sec) | Upload / form | Mandatory | Week 2 Thursday, 10:00 AM | Week 2 Friday | CEM | Must-do #3 · Due Friday of that week (finalized). | Week 2 Fri
T21 | Progress tracker report | Task | Optional | Week 2 Monday, 10:00 AM | Week 2 Tuesday, 9:00 PM IST | CEM | Before Progress Check | Week 2 Tue, 9:00 PM
T22 | Questions for Progress Check | Task | Optional | Week 2 Tuesday, 7:00 PM | Week 2 Wednesday, 5:00 PM IST (before Progress Check) | — |  | Week 2 Wed, 5:00 PM
T23 | Guiding Star | Task | Optional | Week 3 Thursday, 10:00 AM | Week 3 Friday, 9:00 PM IST | CEM |  | Week 3 Fri, 9:00 PM
T24 | Journey deck (PPT): B-HAG + 5 Rituals transformation | Upload | Optional | Week 4 Monday, 10:00 AM | Week 4 Friday, 9:00 PM IST | PL or CEM | Graduation journey | Week 4 Fri, 9:00 PM
T25 | Quiz / assessment (finalise with Arshi) | Quiz | Optional | Week 1 Monday, 10:00 AM | Week 4 Friday, 9:00 PM IST | Auto | Open — confirm with Arshi | Week 4 Fri, 9:00 PM
T26 | Daily ritual check-in (5 Rituals) | Daily | Optional | Week 1 Monday, 7:00 AM (daily from here) | Week 4 Saturday, 11:59 AM IST (back-fill cut-off; score at 12:00 PM) | Auto | Score Sat; does not block certificate unless PL says so | Week 4 Sat, 11:59 AM
T27 | ERRC table | Task | Optional | Week 3 Monday, 10:00 AM | Week 3 Friday, 9:00 PM IST | CEM |  | Week 3 Fri, 9:00 PM
Do by rewritten from LEP_FLOW.pdf v1.5 section 5. Reminder: due-day 10:00 AM + next day 10:00 AM if not done. Week 0 Saturday = Day 1 for the batch. All times IST; move with batch calendar.