# LEP go-live week — Yaswanth & Varun

Dates: Monday 12 Oct 2026 → Saturday 17 Oct 2026

Milestones: Thursday morning — presentation & review with Suvarna and Rajesh · Friday — final demo · Saturday — LIVE for pilot batch.

Split in plain words: Yaswanth owns what the learner sees and does in the app. Varun owns login, Zoho, reminders sending, and backend. Both join Thursday review and Friday demo.

# Who owns what (overall)

| Person | Owns | Examples |
| --- | --- | --- |
| Yaswanth | Learner experience (app screens + journey) | LEP home stages, tasks list, rituals check-in, weekly score screen, B-HAG / CoDeSeF on home, Program Journey wording, session calendar UI for CEM, content shown on tasks, dry-run as learner |
| Varun | Systems that make it work (backend + send) | Phone login / Zoho access, Cloud Functions deploy, notification scheduler, WhatsApp + push sending, CEM alerts C01–C24, Storage/Firestore rules check, CMS save/upload reliability, EAS/env for OTP |
| Together | Reviews & go-live | Thu presentation with Suvarna & Rajesh, Fri final demo, Sat live + hotfixes |
| CEM / PL | Pilot batch truth | Batch name, Day 1 date, Zoom links, approve reminder tone, sign-off Sat |

# Day-by-day — who does what

| Date | Yaswanth | Varun | End of day |
| --- | --- | --- | --- |
| Mon 12 Oct | • Draft T01–T27 list in plain English (must-do vs optional). • Mark which 3 are mandatory (VIA, B-HAG, Pitch). • Align home stages copy with Simple Guide. • With CEM: lock pilot batch name + Day 1 Saturday. | • Prove CMS can save a message and upload a file. • Fix Functions deploy; confirm phone → Zoho access works. • Add C24 / optional-session rules into admin defaults. • Confirm WhatsApp OTP / API keys for staging. | Mapping agreed · CMS write works · pilot batch named |
| Tue 13 Oct | • Session calendar screen for CEM (dates, times, join links). • Enter / help CEM enter pilot S0–S13 times. • B-HAG form + Day 2 CoDeSeF download on home. • Change “course” wording to Program Journey on LEP screens. • Wire must-do flags and due dates on tasks in the app. | • Store batch session times so reminders can use them. • Hook task due dates to calendar (not hard-coded). • Ensure lep/ Storage uploads work for a test user. • Prepare staging build for Thu review. | Pilot calendar in system · BHAG/CoDeSeF path works |
| Wed 14 Oct | • Rituals daily check-in UI (5 ticks). • Status home: Registered / Pre-program / Ready / Active / Needs attention. • Show red only for the 3 must-dos when late. • Prepare learner walkthrough slides for Thu (screens + flow). | • Turn on session reminders: tomorrow / 1 hour / 10 min. • Optional FT/PTW: same-day evening + 10 min only. • After-session congrats (joined) + catch-up (missed). • Quiet hours + max 3 messages/day. • Test push + WhatsApp to 1–2 phones. | Test phone gets R-1h/R-10m · home stages visible |
| Thu 15 Oct MORNING Review | PRESENT with Varun to Suvarna & Rajesh: • Learner journey (stages, 3 must-dos, rituals). • What app sends vs what CEM still calls. • Live click-through of home + rituals + calendar. • Capture feedback in writing before lunch. | PRESENT with Yaswanth: • How reminders will fire from batch times. • Demo a real test reminder if ready. • Risks & what is still human (calls, poster). • Afternoon: apply Suvarna/Rajesh feedback (P0 only). | Review done · P0 feedback list owned · no new scope |
| Thu 15 Oct AFTERNOON | • Fix UI/copy from morning review. • Welcome / pre-work checklist polish. • Attach published content on task screens. • Rehearse Friday demo script (10–12 min). | • Welcome + payment reminder on join. • Task due / overdue + must-do overdue → CEM alert. • Rituals morning + evening nudges. • Start CEM digest alerts (C01, C11 sample). | P0 review fixes in · Fri demo script locked |
| Fri 16 Oct FINAL DEMO | FINAL DEMO (with Varun) for Suvarna, Rajesh, CEM/PL: 1) New learner join → home stage. 2) Pre-work + B-HAG. 3) Rituals tick. 4) Session reminder received. 5) Must-do late → red + CEM alert. Afternoon: only bug fixes from demo. No new features. | FINAL DEMO support: • Trigger test reminders live in the room. • Show CEM alert (email/inbox). • Confirm Functions + WhatsApp healthy. Afternoon: P0 fixes only; freeze for Saturday. | Demo accepted · freeze for live · CEM dry-run done |
| Sat 17 Oct LIVE | • Run learner E2E checklist on pilot batch. • Support CEM walking the home screen. • Hotfix UI only if blocking. • Write 5-line “what is live today” note for the team. | • Flip pilot batch to LIVE. • Monitor first real reminders. • Hotfix send/login only if blocking. • Confirm C01 fires on any new join. | PILOT LEP LIVE — signed by PL/CEM |

# Thursday morning — presentation & review (Suvarna + Rajesh)

Suggested length: 25–30 minutes. Both Yaswanth and Varun present.

| Mins | Who speaks | What to show |
| --- | --- | --- |
| 0–3 | Either | Goal of the week: pilot LEP live by Sat 17 Oct |
| 3–12 | Yaswanth | Learner flow: stages, 3 must-dos, rituals, calendar (click the app) |
| 12–18 | Varun | Reminders: what is automatic; CEM still calls; one live test message if possible |
| 18–22 | Yaswanth | App vs CEM table (from Simple Guide) — one slide |
| 22–30 | Both | Q&A; write P0 changes only; confirm Fri demo time |

Bring: Simple Guide PDF/Word, pilot batch calendar, 1 test phone with app installed.

# Friday — final demo script

1. Join as a new / test learner (Varun triggers if needed).

2. Show home stage and pre-work (Yaswanth).

3. Complete or open B-HAG; show CoDeSeF download entry (Yaswanth).

4. Tick today’s rituals (Yaswanth).

5. Show a session reminder that already arrived or trigger one (Varun).

6. Mark a must-do as late → red on home + CEM gets alert (both).

7. CEM view: one digest / new-join alert (Varun).

8. Ask for go / no-go for Saturday live (Suvarna / Rajesh / PL).

# Saturday — live checklist (sign-off)

| # | Check | Y / V | OK? |
| --- | --- | --- | --- |
| 1 | Pilot batch calendar + join links filled | Y + CEM |  |
| 2 | Test learner can log in and see LEP home stage | V + Y |  |
| 3 | Session reminder received on test phone | V |  |
| 4 | Rituals can be ticked and saved | Y |  |
| 5 | Must-do overdue shows in red | Y |  |
| 6 | CEM received at least one alert (new join or digest) | V |  |
| 7 | PL/CEM verbal or written: “Batch can run on app” | CEM/PL |  |

# Daily stand-up (15 min)

Every morning 12–16 Oct: Yaswanth + Varun — (1) what shipped yesterday, (2) blocker, (3) today. After Thu review: only P0 from Suvarna/Rajesh.

Thu AM: review with Suvarna & Rajesh · Fri: final demo · Sat 17 Oct: LEP pilot LIVE